## Estimate
Zfort Group - IT Outsourcing: Web Development, Consulting & B2B Solutions since 2000 www.zfort.com ¦ contact@zfort.com +1 718 395 7777 ¦ +44 020 8144 5411
Project estimate
Feature / Module Name | Optimistic | Realistic | Notes / Comments
Graphic Design/Mockups
Home Page
Sub Pages
Front-end Development
HTML/CSS/JS coding
Cross-browser optimization
Development
Planning
Gathering information about the system and functionality | 8 | 12
Planning generl architecure of system | 4 | 6
Research of completed extensions, addons | 3 | 5
Splitting development plan into stages | 1 | 2
Splitting stages into tasks | 4 | 5
Preparation
Dev and staging environment setup | 2 | 3
Database Design with high-load approach (sharding, participation) | 6 | 9 | Need to create high-load architecture of database. Make participation of users table, make NoSql layer for authorization and storing in json format data about user for decrease load main database. Also as thing use postgreSQL for forum, because this database not so limited as mysql and can withstand biggest load than mysql
Deployment to production server | 1 | 2
Splitting into tasks between developers | 1 | 3
Development
Core of system in Yii framework with basic idea of API access for 2 ways binding SHOP, Main site with tests, forum | 32 | 40 | Need to create API core with 2 ways synchronization, for example: authorization start from shop then goes to API then update statuses of user in (shop,forum,site) together and this is must be stored and readed from NoSQL storage. Also we can make updating native tables by cron with specific interval. Regarding tests tables — idea is the same. This is basic and main part of project, which will serve as an interlayer between the remaining resources, and reduce the load on the database server. Thereby eliminating the current problems of falling servers and overloads. It is also will be easy to scale as will be created on Yii framework.
Development backend of main site in Yii framework | 120 | 140 | This is also will be developed on Yii framework. In this part of project will be made a lot of ,modules for statistics and managing content of shop. For getting full information we need full requirements that will describe all needs for easy management this resource.
Development frontend of main site with testing module (english language tests), SEO url (custom full path routing) module, multicategory module in Yii framework | 200 | 260 | Site must be created in Yii framework. SEO module — this able us to avoid 301 redirects if we made full path routing. For example we have this link: site.com/tests/category/1/view/id/1 an we can write specific path like: /tests/toefl.html etc. All links we can extract from live site with some grabber. In the end we will be able to save positions in google etc. Also it will be easy to add modifications and increasing the functionality if need.
Development shop backend in Yii framework | 40 | 50 | Just full implementation of current version http://shop.english-test.net/ We will propose to use native Yii backend. This allow us to quickly build any needed parts and extensions across Yii tools. Therefore all code and architecture will be identical in the basic idea of framework.
Development shop frontend light-weight functionality with categories and paypal, CO2 payments | 40 | 60 | Just full implementation of current version http://shop.english-test.net/admin/ In Yii framework. This will be easy to build and support. Why Yii — because this framework have long therm support and can be updated for latest release.
Forum phpBB3 integration, implementation of sound record modules and creating modules for high-load database structure support, maybe postgreSQL | 180 | 200 | In this part we propose to use latest phpBB3 forum cms, because this is clean and stable version that support modu;es and extensions development which in turn allows us to make own extensions and make regular updates of cms without problems, because we dont change any cms core file. Regarding soundrecord — we propose two ways: get existing module and implement it to new version of site, but this can be not good, also we propose to research for new modules off soundrecording that will be more stable and easy to integration.
Quality Assurance
Quality assurance | 97 | 120
Project Management
Project management | 148 | 184
Estimated Total Project Time | 887 | 1101
Estimate | 22175 | 27525
Possible extra costs: images if purchased on image stock websites (photos, illustrations).
Additional Information: